## README
DMAF Migration Wave Planning Workbook
Purpose
This workbook helps plan migration waves for Databricks-led modernization. It supports DMAF-CAP-MGF-001 — Migration Wave Planning and connects candidate inventory, complexity, dependencies, delivery capacity, wave sequencing, and executive summary metrics.
Workbook Section | Purpose
Candidates | Score and assign modernization candidates to migration waves.
Wave Plan | Define wave objectives, timing, scope, and readiness.
Capacity | Capture delivery capacity assumptions by role.
Dependencies | Track candidate-to-candidate dependencies and blockers.
Dashboard | Summarize wave distribution, complexity, effort, and readiness.
Reference Lists | Dropdown values used across the workbook.
Usage Guidance
1. Populate the Candidates sheet with applications, workloads, scores, and initial wave assignments.
2. Use Composite Score and Complexity Band to inform wave sequencing; do not treat them as automatic decisions.
3. Update the Wave Plan with dates, objectives, entry criteria, exit criteria, and governance notes.
4. Capture delivery capacity and unresolved dependencies before committing wave dates.
5. Review the Dashboard before executive or steering updates.
6. Use the workbook as a planning accelerator, not as a replacement for architecture and delivery judgment.

## Candidates
Candidate ID | Application | Workload / Workflow | Source Platform | Business Priority (1-5) | Technical Complexity (1-5) | Dependency Risk (1-5) | Validation Complexity (1-5) | Readiness (1-5) | Business Criticality | Coexistence Need | Estimated Effort Days | Composite Score | Complexity Band | Recommended Wave | Assigned Wave | Status | Owner | Notes
CAND-001 | Customer Analytics | Daily Customer Mart Load | Informatica | 5 | 3 | 3 | 3 | 4 | High | Yes | 20 | 3.4 | High | Wave 2 | Wave 1 | Planned | Migration Lead | Strong business value; manageable complexity.
CAND-002 | Finance Ledger | Monthly GL Extract | Mainframe | 5 | 5 | 5 | 5 | 2 | Critical | Yes | 45 | 4.9 | Very High | Wave 3 | Wave 3 | Planned | Data Architect | High validation and downstream impact.
CAND-003 | Sales Reporting | Sales Summary Pipeline | SSIS | 4 | 2 | 2 | 2 | 5 | Medium | No | 12 | 2.4 | Medium | Wave 1 | Wave 1 | Planned | Developer | Good candidate for early wave.
CAND-004 | Risk Data Hub | Risk Exposure Batch | Oracle ETL | 4 | 4 | 4 | 4 | 3 | High | Yes | 32 | 3.9 | High | Wave 2 | Wave 2 | Planned | Solution Architect | Dependency review required.
CAND-005 | Marketing Data Mart | Campaign Performance Load | Custom SQL | 3 | 2 | 2 | 2 | 4 | Medium | No | 10 | 2.25 | Medium | Wave 1 | Wave 1 | Planned | Developer | Candidate for pattern reuse.

## Wave Plan
Wave | Wave Name | Target Start | Target End | Objective | Candidate Count | Effort Days | Avg Score | High/Very High Count | Status | Entry Criteria | Exit Criteria | Key Risks / Notes
Wave 0 | Reference Implementation / Pilot | 2026-07-01 | 2026-07-31 | Validate patterns and delivery approach. | 0 | 0 | 0 | 0 | Planned | Pilot scope approved; environment ready. | Pattern validated; validation approach confirmed.
Wave 1 | Early Value Wave | 2026-08-01 | 2026-09-14 | Migrate lower complexity, high-value candidates. | 3 | 42 | 2.6833 | 1 | Planned | Candidates ready; dependencies manageable. | Wave candidates validated and accepted.
Wave 2 | Foundation Expansion Wave | 2026-09-15 | 2026-11-13 | Expand to medium/high complexity workloads. | 1 | 32 | 3.9 | 1 | Planned | Patterns stable; capacity confirmed. | Execution metrics within tolerance.
Wave 3 | Complex Workload Wave | 2026-11-14 | 2027-02-06 | Migrate high-complexity, high-dependency workloads. | 1 | 45 | 4.9 | 1 | Planned | Coexistence and validation plan approved. | Readiness gates passed.
Wave 4 | Optimization / Remaining Scope | 2027-02-07 | 2027-04-17 | Complete remaining workload migration and optimization. | 0 | 0 | 0 | 0 | Not Started | Prior waves stable. | Remaining scope closed.
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0

## Capacity
Role | FTE | Available Days / Month | Productivity Factor | Effective Capacity Days | Primary Wave Focus | Notes
Migration Lead | 1 | 18 | 0.8 | 14.4 | All Waves | Governance, sequencing, delivery oversight
Solution Architect | 0.5 | 10 | 0.8 | 4 | Wave 0-2 | Architecture and pattern review
Data Architect | 1 | 18 | 0.75 | 13.5 | Wave 1-3 | Data modeling, dependencies, validation
Developer | 2 | 36 | 0.8 | 57.6 | Wave 1-4 | Migration execution
QA Analyst | 1 | 18 | 0.75 | 13.5 | Wave 1-4 | Testing and validation
Platform Lead | 0.5 | 10 | 0.7 | 3.5 | Wave 0-4 | Environment and operations readiness
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dependencies
Dependency ID | Predecessor Candidate ID | Successor Candidate ID | Dependency Type | Description | Impact | Status | Owner | Target Resolution Date | Notes
DEP-001 | CAND-001 | CAND-004 | Data | Customer data feed required before risk aggregation validation. | High | In Progress | Data Architect | 2026-08-15
DEP-002 | CAND-002 | CAND-004 | Downstream | Finance ledger output impacts risk reporting reconciliation. | Critical | Planned | Test Manager | 2026-09-15
DEP-003 | CAND-003 | CAND-005 | Schedule | Shared reporting window and batch dependency. | Medium | Not Started | Migration Lead | 2026-07-31

## Dashboard
DMAF Migration Wave Planning Dashboard
Metric | Value |  | Wave | Candidate Count | Effort Days
Total Candidates | 5 |  | Wave 0 | 0 | 0
Assigned Candidates | 5 |  | Wave 1 | 3 | 42
Unassigned Candidates | 0 |  | Wave 2 | 1 | 32
Total Estimated Effort Days | 119 |  | Wave 3 | 1 | 45
Average Composite Score | 3.37 |  | Wave 4 | 0 | 0
High / Very High Candidates | 3 |  | Unassigned | 0 | 0
Open Critical Dependencies | 1
Complexity Band | Count | Effort Days
Low | 0 | 0
Medium | 2 | 22
High | 2 | 52
Very High | 1 | 45

## Reference Lists
Source Platform | Score | Business Criticality | Yes/No | Status | Wave | Complexity Band | Dependency Type | Impact | Role
Informatica | 1 | Low | Yes | Not Started | Wave 0 | Low | Data | Low | Engagement Lead
Mainframe | 2 | Medium | No | Planned | Wave 1 | Medium | Application | Medium | Solution Architect
SSIS | 3 | High | Unknown | In Progress | Wave 2 | High | Schedule | High | Data Architect
DataStage | 4 | Critical |  | Blocked | Wave 3 | Very High | Environment | Critical | Migration Lead
Hadoop | 5 |  |  | Complete | Wave 4 |  | Downstream |  | Developer
Teradata |  |  |  | Deferred | Wave 5 |  | SME |  | QA Analyst
Oracle ETL |  |  |  |  | Unassigned |  | Validation |  | Platform Lead
Custom SQL | [6 empty] | Other |  | SME
Other